## Consultancy
Description | Reference No. | Category - Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Invitation Date | Opening Date | Evaluation Date | Approval Date | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
Executive Office
Consultancy service to support establishment and running of pooled procurement mechanism (development of pooled procurement architecture) | ACDC/EO/C/01 | CS | QCBS | OC | 300000 | WB | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultancy service to facilitate Tech transfer mechanisms to match providers and recipients - the consultant will develop an imlementation plan , TOR for the personnel, capacity building, support for local manufacturers in getting tech transfer and matching provider and recipient | ACDC/EO/C/02 | CS | QCBS | OC | 300000 | WB | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultancy Services to Support development of M&E policy, M&E plan & frameworks, data collection, analysis & reporting guidelines and standards | ACDC/EO/C/03 | CS | IC | OC | 54000 | WB | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Develop key policy guidelines; resource mobilization and partner management | ACDC/EO/C/04 | CS | IC | OC | 79200 | WB | 2023-08-01 | 2023-08-06 | 2023-09-05 | 2023-09-26 | 2023-10-03 | 2023-10-08 | 2023-10-15 | 2023-10-22 | 2023-10-29 | 2023-11-05
Division of Disease Control and Prevention
Recruitment of a consultant for the development of a strategic plan (for prioritization, drafting, and validation of the strategy plan) as well as the implementation and M&E plan for Community Health Systems CHWS. | ACDC/DCP/C/05 | CS | IC | OC | 79200 | WB | 2023-04-20 | 2023-04-25 | 2023-05-25 | 2023-06-15 | 2023-06-22 | 2023-06-27 | 2023-07-04 | 2023-07-11 | 2023-07-18 | 2023-07-25
Development of Africa CDC Strategic plan for Endemic and Neglected tropical diseases 2023-2027 | ACDC/DCP/C/06 | CS | IC | OC | 85200 | WB | 2023-03-15 | 2023-03-20 | 2023-04-19 | 2023-05-10 | 2023-05-17 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
Consultancy services to develop training package for endemic diseases and conducting capacity building workshops for health professionals from 55 countries | ACDC/DCP/C/07 | CS | IC | OC | 100000 | MS | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultancy services to conduct sero-surveys for endemic diseases such as viral hepatitis in 10 MS | ACDC/DCP/C/08 | CS | IC | OC | 100000 | MS | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultancy services to support MS with establishing surveillance systems for endemic and NTDs | ACDC/DCP/C/09 | CS | IC | OC | 100000 | MS | 2023-04-01 | 2023-04-06 | 2023-05-06 | 2023-05-27 | 2023-06-03 | 2023-06-08 | 2023-06-15 | 2023-06-22 | 2023-06-29 | 2023-07-06
Emergency Preparedness and Response
Consultancy services for an editor to write COVID-19 report on supply chain support 2020 to 2022 | ACDC/EPR/C/20 | CS | IC | OC | 20000 | AFDB | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Procurement of Consultance service on operationalization of warehouse facility | ACDC/EPR/C/21 | CS | IC | OC | 12000 | AFDB | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultancy services for the development of the Emergency Response Framework for Emergency Preparedness and Response. | ACDC/EPR/C/22 | CS | IC | OC | 50000 | AFDB | 2023-04-01 | 2023-04-06 | 2023-05-06 | 2023-05-27 | 2023-06-03 | 2023-06-08 | 2023-06-15 | 2023-06-22 | 2023-06-29 | 2023-07-06
Conduct continental hazard and threats mapping across Africa for Atlas Project | ACDC/EPR/C/23 | CS | IC | OC | 50000 | WB | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Recruitment/Deployment of 7 consultant in 7 selected MS for 3 months to establish and operationalise Public Health Emergency Operations Centre to enhance coordination of public health emergencies | ACDC/EPR/C/46 | CS | IC | OC | 210000 | AFDB | 2023-05-05 | 2023-05-10 | 2023-06-09 | 2023-06-30 | 2023-07-07 | 2023-07-12 | 2023-07-19 | 2023-07-26 | 2023-08-02 | 2023-08-09
Laboratory Systems and Networks
None
Public Health Policy Diplomacy and Communications
Consultancy Services to implement rumour tracking system | ACDC/PHPD/C/24 | CS | IC | OC | 75000 | WB | 2023-04-02 | 2023-04-07 | 2023-05-07 | 2023-05-28 | 2023-06-04 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07
Hire consultant (multimedia production company) to support content creation for Africa CDC public health campaigns | ACDC/PHPD/C/25 | CS | IC | OC | 40000 | MS | 2023-04-02 | 2023-04-07 | 2023-05-07 | 2023-05-28 | 2023-06-04 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07
Public Health Institutes and Research
Consultancy Servcies to support the implementation of the African Epidemic Service (AES) Programme | ACDC/PHR/C/26 | CS | IC | OC | 120000 | WB | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultancy Services to support NPHIs establishment and strengthening on North Africa | ACDC/PHR/C/27 | CS | IC | OC | 96000 | WB | 2023-04-01 | 2023-04-06 | 2023-05-06 | 2023-05-27 | 2023-06-03 | 2023-06-08 | 2023-06-15 | 2023-06-22 | 2023-06-29 | 2023-07-06
Renewal of the contracts for NPHIs 4 individual consultants | ACDC/PHR/C/28 | CS | IC | DC | 192000 | AFDB | 2023-06-01 | 2023-06-06 | 2023-07-06 | 2023-07-27 | 2023-08-03 | 2023-08-08 | 2023-08-15 | 2023-08-22 | 2023-08-29 | 2023-09-05
Consutancy service to to support the Africa CDC Learning management System (LMS) | ACDC/PHR/C/29 | CS | IC | OC | 72000 | US CDC | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Division of Surveillance and Disease Intelligence
Procurement of consultancy services to develop Africa CDC EBS staff competence framework | ACDC/SDI/C/30 | CS | IC | OC | 49800 | World Bank | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Recruitment of a consultant to develop the Africa CDC continental Cross Border Surveillance Strategy/ Framework | ACDC/SDI/C/31 | CS | IC | OC | 79200 | World Bank | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
External Consultants to support the TA to countries for One HEALTH and AMR | ACDC/SDI/C/32 | CS | IC | OC | 50000 | World Bank | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultant to develop and implement communication and advocacy for WAAW 2023 | ACDC/SDI/C/33 | CS | IC | OC | 30000 | US CDC | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultant to review National Action Plans on AMR for 5 MS | ACDC/SDI/C/34 | CS | IC | OC | 30000 | US CDC | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
External Consultant to support the TA to countries for Mortality Surveillance | ACDC/SDI/C/35 | CS | IC | OC | 50000 | World Bank | 2023-03-01 | 2023-03-14 | 2023-04-13 | 2023-05-04 | 2023-05-11 | 2023-05-16 | 2023-05-23 | 2023-05-30 | 2023-06-06 | 2023-06-13
Development of mortality surveillance implementation standards, guidelines, SOPs & tools | ACDC/SDI/C/36 | CS | IC | OC | 50000 | World Bank | 2023-03-01 | 2023-03-14 | 2023-04-13 | 2023-05-04 | 2023-05-11 | 2023-05-16 | 2023-05-23 | 2023-05-30 | 2023-06-06 | 2023-06-13
External Consultant to support the development of digital system and integration for mortality data repository | ACDC/SDI/C/37 | CS | IC | OC | 80000 | World Bank | 2023-03-01 | 2023-03-14 | 2023-04-13 | 2023-05-04 | 2023-05-11 | 2023-05-16 | 2023-05-23 | 2023-05-30 | 2023-06-06 | 2023-06-13
Consultancy Services to Increase capacity of Africa CDC and its regional platforms to collect, analyze, and disseminate continent-wide data | ACDC/SDI/C/38 | CS | QCBS | OC | 877000 | AFDB | 2023-02-15 | 2023-02-28 | 2023-03-30 | 2023-04-20 | 2023-04-27 | 2023-05-02 | 2023-05-09 | 2023-05-16 | 2023-05-23 | 2023-05-30
Division of Management and Administration
Consultancy Services to Re-engineering of Operations Support Services and Business Process of the Africa CDC and Development of SOPs, Guidelines and Risk Management Framework | ACDC/MA/C/39 | CS | QCBS | OC | 500000 | World Bank | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
Consultancy services to develop and build organizational culture on core values, Safeguarding, SEAH and E&S (environmental & social) framework and guidelines | ACDC/MA/C/40 | CS | QCBS | OC | 300000 | World Bank | 2023-04-01 | 2023-04-06 | 2023-05-06 | 2023-05-27 | 2023-06-03 | 2023-06-08 | 2023-06-15 | 2023-06-22 | 2023-06-29 | 2023-07-06
Develop Finance management workflow system | ACDC/MA/C/41 | CS | IC | OC | 15000 | World Bank | 2023-03-20 | 2023-04-02 | 2023-05-02 | 2023-05-23 | 2023-05-30 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02
Development of Real time reporting module for Finance | ACDC/MA/C/42 | CS | IC | OC | 15000 | World Bank | 2023-04-28 | 2023-05-11 | 2023-06-10 | 2023-07-01 | 2023-07-08 | 2023-07-13 | 2023-07-20 | 2023-07-27 | 2023-08-03 | 2023-08-10
Implement e-Travel management | ACDC/MA/C/43 | CS | QCBS | OC | 200000 | World Bank | 2023-05-01 | 2023-05-06 | 2023-06-05 | 2023-06-26 | 2023-07-03 | 2023-07-08 | 2023-07-15 | 2023-07-22 | 2023-07-29 | 2023-08-05
Implement e-Procurement | ACDC/MA/C/44 | CS | DC | OC | 200000 | World Bank | 2023-06-01 | 2023-06-06 | 2023-07-06 | 2023-07-27 | 2023-08-03 | 2023-08-08 | 2023-08-15 | 2023-08-22 | 2023-08-29 | 2023-09-05
Consultancy Services to support the Recuritement porcess of Africa CDC to onboard staff | ACDC/MA/C/45 | CS | QCBS | OC | 91000 | World Bank | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05
[8 empty] | 1900-01-04 | 1900-02-03 | 1900-02-24 | 1900-03-03 | 1900-03-08 | 1900-03-15 | 1900-03-22 | 1900-03-29 | 1900-04-05
[8 empty] | 1900-01-04 | 1900-02-03 | 1900-02-24 | 1900-03-03 | 1900-03-08 | 1900-03-15 | 1900-03-22 | 1900-03-29 | 1900-04-05
Total |  |  |  |  | 4751600

## Goods
Description (Value cannot exceed 250 Characters) | Reference No. | Category - Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Invitation Date | Opening Date | Evaluation Date | Approval Date | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
Executive Office
Procurement of office furniture to set up up of R&D coordinating platform in all the five regions | ACDC/EO/G/01 | GO | RFQ | LC | 46000 | WB | 2023-03-01 | 2023-03-06 | 2023-04-05 | 2023-04-26 | 2023-05-03 | N/A | N/A | N/A | 2023-05-10 | 2023-05-17
Procurement of Laptop and docking station for Project Staff | ACDC/EO/G/02 | GO | RFQ | LC | 12000 | WB | 2023-06-01 | 2023-06-06 | 2023-07-06 | 2023-07-27 | 2023-08-03 | N/A | N/A | N/A | 2023-08-10 | 2023-08-17
Division of Disease Control and Prevention
None | [7 empty] | 1900-01-04 | 1900-02-03 | 1900-02-24 | 1900-03-03 | N/A | N/A | N/A | 1900-03-10 | 1900-03-17
Emergency Preparedness and Response
Procurement of 4 Division phones | ACDC/EPR/G/03 | GO | RFQ | LC | 4000 | AFDB | 2023-04-01 | 2023-04-06 | 2023-04-13 | 2023-05-04 | 2023-05-11 | N/A | N/A | N/A | 2023-05-18 | 2023-05-25
Procurement of Africa CDC-AVoHC Promotional Materials | ACDC/EPR/G/04 | GO | RFQ | LC | 97000 | MS & AFDB | 2023-04-01 | 2023-04-06 | 2023-04-13 | 2023-05-04 | 2023-05-11 | N/A | N/A | N/A | 2023-05-18 | 2023-05-25
Procurement of 1000 first aid kits for AVoHC deployment | ACDC/EPR/G/05 | GO | RFB | OC | 100000 | MS | 2023-04-20 | 2023-04-25 | 2023-05-25 | 2023-06-15 | 2023-06-22 | N/A | N/A | N/A | 2023-06-29 | 2023-07-06
Procurement of PHEOC ICT equipment for the operationalization of the PHEOC in selected MS | ACDC/EPR/G/06 | GO | RFB | OC | 2830000 | AFDB | 2023-04-01 | 2023-04-06 | 2023-05-06 | 2023-05-27 | 2023-06-03 | N/A | N/A | N/A | 2023-06-10 | 2023-06-17
Procurement of hardware and ICT equipments for Africa CDC warehouses in Douala and AUC HQ | ACDC/EPR/G/07 | GO | RFB | OC | 1160000 | AFDB | 2023-05-03 | 2023-05-08 | 2023-06-07 | 2023-06-28 | 2023-07-05 | N/A | N/A | N/A | 2023-07-12 | 2023-07-19
Laboratory Systems and Networks
Procurement of Tablets for laboratory mapping data collection | ACDC/LSN/G/08 | GO | RFQ | LC | 15000 | Member States | 2023-05-01 | 2023-05-06 | 2023-05-13 | 2023-06-03 | 2023-06-10 | N/A | N/A | N/A | 2023-06-17 | 2023-06-24
Procurement of test kits, sample collection, packaging and transportation materials | ACDC/LSN/G/09 | GO | RFB | OC | 720000 | Member States | 2023-05-02 | 2023-05-07 | 2023-06-06 | 2023-06-27 | 2023-07-04 | N/A | N/A | N/A | 2023-07-11 | 2023-07-18
Equipment and reagents procurement to support Africa PGI efforts in selected Member countries (MiSeq System (02), COVIDSeq Assay 96 samples (18), IDT® for Illumina PCR Indexes Sets 1-4 (18), Illumina COVIDSeq v4 Primer Pools, 384 RUO Samples (18), and MiSeq® Reagent Kit v3 (600 cycle) (18)) | ACDC/LSN/G/10 | GO | RFB | OC | 1085600 | AfDB | 2023-06-01 | 2023-06-06 | 2023-06-13 | 2023-07-04 | 2023-07-11 | N/A | N/A | N/A | 2023-07-18 | 2023-07-25
Procurement of testing and sequencing reagents, supplies, and consumables for 2000 Mpox specimens across Africa | ACDC/LSN/G/11 | GO | RFB | OC | 500000 | Canada Gov't | 2023-05-01 | 2023-05-06 | 2023-06-05 | 2023-06-26 | 2023-07-03 | N/A | N/A | N/A | 2023-07-10 | 2023-07-17
Public Health Research and Institutes
Procurement of Laptop and docking station for AES trainees | ACDC/PHIR/G/12 | GO | RFQ | LC | 50000 | WB | 7 Aug 2023 | 2023-08-12 | 2023-08-19 | 2023-09-09 | 2023-09-16 | N/A | N/A | N/A | 2023-09-23 | 2023-09-30
Division of Surveillance and Disease Intelligence
Procure high spec laptops for RCC and HQ EBS staff and Cross border surveillance program staff | ACDC/SDI/G/13 | GO | RFB | OC | 35000 | WB | 2023-04-04 | 2023-04-09 | 2023-05-09 | 2023-05-30 | 2023-06-06 | N/A | N/A | N/A | 2023-06-13 | 2023-06-20
Division of Management and Administration
Procurement of IT Equipment to support Automation of Administration and management process (Operations and Support Services) | ACDC/MA/G/14 | GO | RFB | OC | 300000 | WB | 2023-09-01 | 2023-09-06 | 2023-09-13 | 2023-10-04 | 2023-10-11 | N/A | N/A | N/A | 2023-10-18 | 2023-10-25
Procurement of IT Equipment and Furniture for Finance Unit | ACDC/MA/G/15 | GO | RFQ | LC | 26000 | WB | 2023-03-15 | 2023-03-20 | 2023-03-27 | 2023-04-17 | 2023-04-24 | N/A | N/A | N/A | 2023-05-01 | 2023-05-08
Puplic Health Policy Diplomacy and Communications
Purchasing software licenses and subscriptions | ACDC/MA/G/16 | GO | RFQ | LC | 35000 | MS | 2023-06-01 | 2023-06-06 | 2023-06-13 | 2023-07-04 | 2023-07-11 | N/A | N/A | N/A | 2023-07-18 | 2023-07-25
Total |  |  |  |  | 7015600
Formulas:
Invitation Date = [Request Submission Date]+5
Opening Date = [Invitation Date]+30
Evaluation Date = [Opening Date]+21
Approval Date = [Evaluation Date]+7
Contract Vetting = [Approval Date]+7
Contract Signing = [Contract Vetting]+7

## Non Consultancy
Description | Reference No. | Category - Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Invitation Date | Opening Date | Evaluation Date | Approval Date | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
Executive Office
None
Division of Disease Control and Prevention
None
Emergency Preparedness and Response
Publication of Papers | ACDC/EPR/NC/01 | NC | RFQ | LC | 20000 | AFDB | 2023-07-01 | 2023-07-06 | 2023-07-13 | 2023-07-23 | 2023-08-02 | 2023-08-05 | 2023-08-10 | 2023-08-20 | 2023-08-27 | 2023-09-06
Maintenance of MAIN PHEOC Lisences and other softwares including subscriptions | ACDC/EPR/NC/02 | NC | RFQ | LC | 100000 | AFDB | 2023-03-01 | 2023-03-06 | 2023-03-13 | 2023-03-23 | 2023-04-02 | 2023-04-05 | 2023-04-10 | 2023-04-20 | 2023-04-27 | 2023-05-07
Subscription to Gideon platform | ACDC/EPR/NC/03 | NC | RFQ | LC | 40000 | AFDB | 2023-06-01 | 2023-06-06 | 2023-06-13 | 2023-06-23 | 2023-07-03 | 2023-07-06 | 2023-07-11 | 2023-07-21 | 2023-07-28 | 2023-08-07
Laboratory Systems and Networks
None | [7 empty] | 1900-01-04 | 1900-01-11 | 1900-02-01 | 1900-02-08 | 1900-02-13 | 1900-02-20 | 1900-02-27 | 1900-02-15 | 1900-02-22
Public Health Research and Institutes
None
Division of Surveillance and Disease Intelligence
None | [7 empty] | 1900-01-04 | 1900-01-11 | 1900-02-01 | 1900-02-08 | 1900-02-13 | 1900-02-20 | 1900-02-27 | 1900-02-15 | 1900-02-22
Public Health Policy Diplomacy and Communications
Branding of Africa CDC press briefing room | ACDC/PHPD/NC/04 | NC | RFQ | LC | 3000
Subscription fees to stream Africa CDC Podcast online | ACDC/PHPD/NC/05 | NC | RFQ | LC | 7500
Division of Management and Administration
[8 empty] | 1900-01-04 | 1900-02-03 | 1900-02-24 | 1900-03-03 | 1900-03-08 | 1900-03-15 | 1900-03-22 | 1900-03-29 | 1900-04-05
Total |  |  |  |  | 170500

## Works
Description | Reference No. | Category - Sourcing | Sourcing Method | Type of Competition | Estimated Amount in US$ | Financed By | Request Submission Date | Invitation Date | Opening Date | Evaluation Date | Approval Date | Opening of Financial Proposal | Combined Evaluation | Approval Date | Contract Vetting | Contract Signing
Division of Disease Control and Prevention
None
Emergency Preparedness and Response
Renovation and installation of Africa CDC's warehouse at CLB douala and AUC HA | ACDC/EPR/NC/001 | W | RFB | OC | 600000 | MS | 2023-04-20 | 2023-04-25 | 2023-05-25 | 2023-06-15 | 2023-06-22 | N/A | N/A | N/A | 2023-06-29 | 2023-07-06
Laboratory Systems and Networks
None
Public Health Research and Institutes
None
Division of Surveillance and Disease Intelligence
None
Division of Management and Administration
None
Total |  |  |  |  | 600000
Formulas:
Invitation Date = [Request Submission Date]+5
Opening Date = [Invitation Date]+30
Evaluation Date = [Opening Date]+21
Approval Date = [Evaluation Date]+7
Contract Vetting = [Approval Date]+7
Contract Signing = [Contract Vetting]+7

## OVER ALL SUMMARY
2023 Revised Procurement Plan
No. | Category | Total Amount (USD)
1 | GOODS | 7015600
2 | CONSULTANCY SERVICES | 4751600
3 | WORKS | 600000
4 | NON-CONSULTANCY SERVICES | 170500
TOTAL |  | 12537700

## Sourcing Methods Mapping
Procurement Category Code | GO | CW | CS | NC | Sourcing Category Code | Sourcing Category Definition | Review Type | Type of Competition Code | Sourcing Type of Competition
GO | RFP | RFP | QCBS | RFP | GO | Goods | Post | OC | Open Competition
CW | RFB | RFB | FBS | RFB | W | Works | Prior | LC | Limited Competition
CS | RFQ | RFQ | LCS | RFQ | CS | Consultant Services |  | DC | Direct Competition
NC | DIR | DIR | QBS | DIR | NC | Non-Consulting Services
| UN | UN | CDS | UN
| EA | CDD | INDV | EA | Sourcing Method Code (CS) | Sourcing Method Definition |  | Sourcing Method Code (GO) | Sourcing Method Definition
| IMP | FCA | UN | CDD | QCBS | Quality and Cost-Based Selection |  | RFP | Request for Proposals
| COMM | APA | NPO | FCA | FBS | Fixed Budget Selection |  | RFB | Request for Bids
| CDD | PPP | BANK | APA | LCS | Least Cost Selection |  | RFQ | Request for Quotations
| APA | CP | PRA | PPP | QBS | Quality Based Selection |  | DIR | Direct Selection
| CP |  | CAPA | CP | CQS | Consultant Qualification Selection |  | UN | UN Agencies (Direct)
|  |  | CCP |  | CDS | Direct Selection
[5 empty] | INDV | Individual Consultant Selection
[5 empty] | UN | UN Agencies (Direct)
[5 empty] | PRA | Procurement Agents
[5 empty] | Sourcing Method Code (W) | Procurement Method Definition |  | Sourcing Method Code (NC) | Procurement Method Definition
[5 empty] | RFP | Request for Proposals |  | RFP | Request for Proposals
[5 empty] | RFB | Request for Bids |  | RFB | Request for Bids
[5 empty] | RFQ | Request for Quotations |  | RFQ | Request for Quotations
[5 empty] | DIR | Direct Selection |  | DIR | Direct Selection
[5 empty] | UN | UN Agencies (Direct) |  | UN | UN Agencies (Direct)
[5 empty] | FCA | Force Account |  | FCA | Force Account
[5 empty] | PPP | Public Private Partnerships |  | PPP | Public Private Partnerships

## Sheet1
2023
Division | Consultancy Services |  | Goods |  | Non-Consultancy Services |  | Works |  | Total
| # | Amount in USD | # | Amount in USD | # | Amount in USD | # | Amount in USD | # | Amount in USD
Executive Office | 4 | 733200 | 2 | 58000 | 0 | 0 | 0 | 0 | 6 | 791200
Division of Disease Control and Prevention | 5 | 464400 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 464400
Emergency Preparedness and Response | 4 | 342000 | 9 | 4191000 | 3 | 160000 | 1 | 600000 | 16 | 4693000
Laboratory Systems and Networks | 0 | 0 | 5 | 2320600 | 0 | 0 | 0 | 0 | 5 | 2320600
Public Health Research and Institutes | 4 | 480000 | 1 | 50000 | 0 | 0 | 0 | 0 | 5 | 530000
Public Health Policy Diplomacy and Communications | 2 | 115000 | 2 | 35000 | 2 | 10500 | 0 | 0 | 6 | 160500
Division of Surveillance and Disease Intelligence | 9 | 1296000 | 1 | 35000 | 0 | 0 | 0 | 0 | 10 | 1331000
Division of Management and Administration | 7 | 1321000 | 2 | 326000 | 0 | 0 | 0 | 0 | 9 | 1647000
| 35 | 4751600 | 22 | 7015600 | 5 | 170500 | 1 | 600000 | 63 | 12537700